## Backlog
ID | Priority | Area | Title | Description | Acceptance Criteria | Status | Owner | Target Release | Notes | GitHub Issue Link
LALA-001 | P0 | Fuel / Pre-grid | Pre-grid fuel warning (one-stint) | Warn before rolling if current fuel cannot finish a no-stop race given profile avg fuel/lap, wet factor, contingency, race length. | Shows deficit > 0 L only in Race sessions; works for lap- or time-based races; exposes SimHub params Lala.Fuel.PreGrid.RequiredFuelL, DeficitL, LowFuel. | Backlog | Andy | v0.4.0
LALA-002 | P0 | Fuel / Stint | Live target fuel + tolerance + confidence | Rolling mean + stddev of fuel/lap; target band ±0.05 L/lap; compute fuel-to-finish & per-lap saving needed; display confidence (Low/Med/High). | Stabilizes within ~5 laps; exposes Lala.Fuel.TargetLPerLap, BandLow, BandHigh, FuelToFinishL, FuelDeltaL, SaveLPerLap, Samples, StdDev, Confidence. | Backlog | Andy | v0.4.0
LALA-003 | P0 | Fuel / Pit prep | Live fuel calculator (pre-pit screen feed) | Compute FuelToAdd with one-lap buffer based on target fuel/lap and laps remaining. Feed SimHub pre-pit dashboard. | Exposes Lala.Fuel.PrePit.FuelToAddL, LapsRemaining, OneLapBufferL; matches Fuel tab strategy math. | Backlog | Andy | v0.4.0
LALA-004 | P0 | Fuel / Post-race | Verify race mining button | Button on Fuel tab to analyze session samples (in-memory), reject outliers, compute race averages, compare to profile, and optionally apply. | Shows clear summary (fuel/lap & lap time deltas); 'Apply' writes just AvgFuelPerLap* and AvgLapTime*; no JSON writes otherwise. | Backlog | Andy | v0.4.0
LALA-005 | P0 | SimHub params | Parameter exposure sweep | Register all new Lala.Fuel.* parameters for dashboards (pre-grid, stint, pre-pit, verify outputs). Update in DataUpdate loop. | All planned params present and stable; documented in README. | Backlog | Andy | v0.4.0
LALA-006 | P0 | Threading/UI | ObservableCollection UI-thread audit | Ensure all adds/clears for CarProfiles & track lists occur on UI dispatcher; mutate collections in place. | No cross-thread exceptions; no list swaps; dispatcher usage documented. | Backlog | Andy | v0.4.0
LALA-007 | P0 | Persistence | Stop persisting temps/sample counts | Keep temps & sample counts in memory only; remove writes in save paths. Maintain backward-compatible loads. | JSON stops changing those fields; Fuel tab still shows live info labels; loads tolerate historic fields. | Backlog | Andy | v0.4.0
LALA-008 | P0 | Engines / Pit | Pit engine uses profile pit loss & fuel numbers | Ensure PitEngine reads ActiveProfile.PitLaneLossSeconds and AvgFuelPerLap(Dry/Wet); unify units and reuse Fuel math. | Pit predictions match Fuel tab; unit tests/spot checks pass; no duplicate calculations. | Backlog | Andy | v0.4.0
LALA-009 | P0 | Engines / Rejoin | Rejoin engine reads ActiveProfile | On live combo change, reattach to ActiveProfile for car/track; no stale references. | Mid-session car switch follows ActiveProfile; logs confirm current context. | Backlog | Andy | v0.4.0
LALA-010 | P0 | Engines / Threat | Threat engine context consistency | Tie threat calculations to ActiveProfile; add car/track to log lines for traceability. | Threat messages include car/track; no mismatched context after apply-to-live. | Backlog | Andy | v0.4.0
LALA-011 | P0 | I/O | Debounce SaveProfiles | If called from hot paths, gate saves with a 500ms debounce to reduce disk churn. | No save spam in logs; no data loss; final write always occurs on state change. | Backlog | Andy | v0.4.0
LALA-012 | P0 | QA | Manual test matrix | Create a repeatable click-path matrix (live/non-live, new/existing car/track, apply, save, pit, rejoin). | Checklist lives in repo; can be run in <10 minutes pre-release. | Backlog | Andy | v0.4.0
LALA-013 | P1 | Strategy | Undercut/overcut delta | Simple simulation using your pace, rival pace, and pit loss to estimate exit delta if boxing now vs staying out. | Exposes Lala.Strat.UnderOverDeltaSec, Recommendation; behaves sanely with obvious scenarios. | Backlog | Andy | v0.5.0
LALA-014 | P1 | Rejoin | Pit-exit gap predictor | Estimate closest car ahead/behind at pit exit and warn if < 0.8s. | Exposes Lala.Rejoin.ExitAheadSec, ExitBehindSec, TrafficWarning; matches existing rejoin behavior. | Backlog | Andy | v0.5.0
LALA-015 | P1 | Profiles | Track maintenance tools | Add/Rename/Delete/Merge tracks (display only); never change keys; fix messy profiles without JSON edits. | All actions available; list refreshes instantly; no key mutations. | Backlog | Andy | v0.5.0
LALA-016 | P1 | UX | Driver vs Engineer mode toggle | Toggle to hide/show advanced controls; driver sees target fuel, fuel-to-add, laps-to-box, PB. | Single toggle flips visibility groups; persists per user; no layout churn. | Backlog | Andy | v0.5.0
LALA-017 | P0 | Telemetry / API | Expose pit phase (Pit.Phase) | Publish current pit cycle phase as idle, pit-lap, or out-lap for use on dashes and testing overlays. | Property is present; shows 'pit-lap' at S/F after pit exit; shows 'out-lap' at S/F after pit box; returns 'idle' otherwise; validated on two replay stops. | Backlog | Andy | v0.4.0
LALA-018 | P0 | Naming / API | Standardise new SimHub property names (drop extra 'Lala.') | For new properties use canonical names without the extra 'Lala.' segment. Keep existing names as aliases for backward compatibility and document the mapping. | New delegates exposed without 'Lala.'; existing dash bindings continue to work; README contains mapping table of old→new names. | Backlog | Andy | v0.4.0
LALA-019 | P0 | Profiles / UX | DTL auto‑fill and candidate apply | If profile pit‑lane loss is empty/0, auto‑fill on first valid stop. Otherwise show 'New candidate: Xs' with an Apply button to commit. Provide a Reset button to default (configurable). | 1) Auto‑fill occurs only when current = 0; 2) Candidate banner appears after valid stop; 3) Apply updates profile and UI; 4) Reset restores default value. | Backlog | Andy | v0.5.0
LALA-020 | P0 | Persistence | Save hygiene tolerance for DTL | Avoid churn by only saving profile pit‑lane loss when ¦new − current¦ ≥ 0.5 s. Log whether save was suppressed or performed, and the source (direct/formula). | Small deltas (<0.5 s) do not write; log shows 'suppressed' vs 'saved' with timestamp and source. | Backlog | Andy | v0.4.0
LALA-021 | P1 | Mining | Mine tyre‑change delta | From stops with wheel changes, estimate tyre‑change time; maintain rolling median and sample count; surface as candidate with Apply button. | Candidate value and sample count shown; Apply writes to profile; confidence displayed. | Backlog | Andy | v0.5.0
LALA-022 | P1 | Mining | Mine refuel rate (L/s) | From fuel‑only stops, compute effective refuel rate; maintain rolling median; ignore mixed tyre+fuel stops that skew the rate; surface as candidate with Apply. | Candidate with sample count visible; Apply persists and it is used by pit‑time calculator. | Backlog | Andy | v0.5.0
LALA-023 | P1 | Telemetry / API | Expose Pit.FormulaTopSec (debug) | Publish (PitLap − Stop + OutLap) as a diagnostic to explain DTL changes across layouts and baselines. | Property equals arithmetic from log within ±0.01 s on two replay stops. | Backlog | Andy | v0.4.0
LALA-024 | P1 | Baseline | Wet/dry baseline selection | When track condition is Wet, prefer profile wet average; otherwise prefer profile dry average; fallback chain remains as today. | Source label shows 'profile‑avg‑wet' or 'profile‑avg'; numbers match profile values. | Backlog | Andy | v0.5.0
LALA-025 | P1 | Docs | Property naming map in README | Add a table that lists canonical property names and deprecated aliases so dashes can transition cleanly. | README contains mapping table and note on deprecation policy. | Backlog | Andy | v0.4.0
LALA-026 | P0 | UI / Dash | Service stop loss (DTL + Stop) property – document and demo | Document the Service stop loss property and include in the sample dash for strategy gap estimation. | Property visible; sample dash updated; validated on replay stops. | Backlog | Andy | v0.4.0
LALA-027 | P1 | UI | Tire change time changing total fuel unecessarily | Changing tire time that is still less than refuel time is adjusting fuel when it shouldn't because the time is already accounted by the refuel time. | When tire change time is less than refuel time, the total fuel needed should not change | Backlog | Andy | any